## Frontend
ID | Task ID | Test Objective | Test Steps | Expected Result | Actual Result | Pass/Fail | Related tasks | Date | Teszt sablon
1 | LG-1 | Test if login works | 1. Go to http://127.0.0.1:5500/login.html 2. Enter the email: existing email 3. Enter the password: abc123 4. Press the login button | Login attempt succeeds. A warn appears that you have successfully logged in | Login attempt succeeds. A warn appears that you have successfully logged in | Pass |  | 2025-11-04 | ID | Task ID | Test Objective | Test Steps | Expected Result | Actual Result | Pass/Fail | Related tasks | Date
2 | LG-2 | Test if login fails uppon giving incorrect password | 1. Go to http://127.0.0.1:5500/login.html 2. Enter the email: existing email 3. Enter a bad password 4. Press the login button | Login attempt fails. A warn appears that the password is incorrect. | Login attempt succeeds. A warn appears that you have successfully logged in | Pass |  | 2025-11-04 | 1 | LG-1 | Test if login works with valid credentials | 1. Navigate to the login page 2. Enter a valid existing email 3. Enter the correct password 4. Press the login button | Login attempt succeeds. A success notification appears. |  |  | LG-2, LG-3, LG-4, LG-5
3 | LG-3 | Test if login fails uppon giving incorrect email | 1. Go to http://127.0.0.1:5500/login.html 2. Enter a bad email: non existing email or smth 3. Enter the password: abc123 4. Press the login button | Login attempt fails. A warn appears that the email is incorrect. | Login attempt fails. A warn appears that the email is incorrect. | Pass |  | 2025-11-04 | 2 | LG-2 | Test if login fails with incorrect password | 1. Navigate to the login page 2. Enter a valid existing email 3. Enter an incorrect password 4. Press the login button | Login attempt fails. An error message indicates incorrect password. |  |  | LG-1, LG-3, LG-4, LG-5
4 | CP-1 | Test if you can change password | 1. Create an account or login to your account if you have one 2. Click on your profile 3. Go to "Profile details" 4. Click on password change 5. Enter your new password 6. Try to login with your new password | Password successfully changes, and the user is able to login with the new password |  | Hold |  | 2025-11-04 | 3 | LG-3 | Test if login fails with non-existing email | 1. Navigate to the login page 2. Enter a non-existing email 3. Enter any password 4. Press the login button | Login attempt fails. An error message indicates the email is not found. |  |  | LG-1, LG-2, LG-4, LG-5
5 | CP-2 | Test if you can restore your password uppon forgetting it | 1. Create an account or login to your account if you have one 2. Log out 3. Go to login page 4. Click on "I forgot my password" 5. Give the new password 6. Try to login with your new password | Password successfully changes, and the user is able to login with the new password |  | Hold |  | 2025-11-04 | 4 | LG-4 | Test if login fails when fields are empty | 1. Navigate to the login page 2. Leave email and password fields empty 3. Press the login button | Login attempt fails. An error message indicates required fields are empty. |  |  | LG-1, LG-2, LG-3, LG-5
6 | RG-1 | Test if you can registrate | 1. Fill the fields out 2. Press the registrate button 3. Check whether the registration is succesful | Registration is succesful, and you get a link on your email, to confirm your registration |  | Hold |  | 2025-11-17 | 5 | LG-5 | Test if login fails with invalid email format | 1. Navigate to the login page 2. Enter an invalid email format (e.g. "notanemail") 3. Enter any password 4. Press the login button | Login attempt fails. An error message appears about invalid email format. |  |  | LG-1, LG-2, LG-3, LG-4
7 | PT-1 | Test if the home button redirecting to home page | 1. press the home button | Upon clicking on the button home page appears | Not found | Fail |  | 2026-01-19 | 6 | RG-1 | Test if user can register a new account | 1. Navigate to the registration page 2. Fill in all fields correctly 3. Press the register button 4. Check email for confirmation link | Registration succeeds and a confirmation email is sent. |  |  | RG-2, RG-3
8 | PT-1 | Test if the home button redirecting to home page | 1. press the home button | Upon clicking on the button home page appears | Page appears | Pass |  | 2026-01-19 | 7 | RG-2 | Test if registration fails with invalid email format | 1. Navigate to the registration page 2. Enter an invalid email format 3. Fill other fields correctly 4. Press the register button | Registration fails. An error message appears about invalid email format. |  |  | RG-1, RG-3
9 | PT-2 | Test if the products button redirecting to products page | 1. press the products button | Upon clicking on the button products page appears | Page appears | Pass |  | 2026-01-19 | 8 | RG-3 | Test if registration fails when required fields are empty | 1. Navigate to the registration page 2. Leave one or more required fields empty 3. Press the register button | Registration fails. Error messages appear for the empty required fields. |  |  | RG-1, RG-2
10 | PT-3 | Test if the forum button redirecting to forum page | 1. press the forum button | Upon clicking on the button forum page appears | Page appears | Pass |  | 2026-01-19 | 9 | AU-1 | Test if logout works correctly | 1. Log in with a valid account 2. Click on the logout button 3. Try to access a protected page | User is logged out and redirected to the login page. |  |  | AU-2, AU-3, LG-1
11 | PR-1 | Test if profile works | 1. press the profile icon | Upon clicking on the profile icon a dropdown appears |  | Hold |  | 2026-01-22 | 10 | AU-2 | Test if user stays logged in after page reload | 1. Log in with a valid account 2. Reload the page | User remains logged in and is not redirected to the login page. |  |  | AU-1, AU-3
12 |  | Test if user can subscribe to newsletter | 1. Press the subscribe to newsletter field 2. Write your email in it 3. press the button and check your emails | Email should be sent which confirms that you have subscribed to the newsletter |  | Hold |  | 2026-01-22 | 11 | AU-3 | Test if unauthorized user is redirected from protected page | 1. Open a protected page URL without logging in | User is redirected to the login page. |  |  | AU-1, AU-2
13 | BT-1 | Test if secondary button works | 1. Press any button that looks green, on the bracket page 2. Check for an event that got attached to it | Secondary button should execute the function onclick. |  | Hold |  | 2026-01-22 | 12 | CP-1 | Test if user can change password from profile | 1. Log in 2. Click on your profile 3. Go to "Profile details" 4. Click on password change 5. Enter new password 6. Log out and log back in with the new password | Password is changed and the user can log in with the new password. |  |  | CP-2, LG-1
14 | SL-1 | Test if slider button "next" works | 1. Press the right arrow button 2. Check if the slider's picture changed | Upon clicking on the "next" button the slider's picture changes | Upon clicking on the "next" button the slider's picture doesn't changes | Fail |  | 2026-01-26 | 13 | CP-2 | Test if user can reset forgotten password via email | 1. Log out 2. Go to login page 3. Click "Forgot my password" 4. Follow the email link 5. Set a new password 6. Log in with the new password | Password is reset and the user can log in with the new password. |  |  | CP-1, LG-1
15 | SL-2 | Test if slider button "previous" works | 1. Press the left arrow button 2. Check if the slider's picture changed | Upon clicking on the "previous" button the slider's picture changes | Upon clicking on the "previous" button the slider's picture doesn't changes | Fail |  | 2026-01-26 | 14 | PT-1 | Test if Home button redirects to the Home page | 1. Press the Home button in the navigation bar | Home page appears. |  |  | PT-2, PT-3
16 | SL-3 | Test if slider's small stepper buttons work | 1. Press the small stepper buttons 2. Check if the slider's picture changed | Upon clicking on the buttons the slider's picture changes | Upon clicking on the buttons the slider's picture doesn't changes | Fail |  | 2026-01-26 | 15 | PT-2 | Test if Products button redirects to the Products page | 1. Press the Products button in the navigation bar | Products page appears. |  |  | PT-1, PT-3
17 | BT-2 | Test if support button works | 1. Press the support button 2. Check if an overlay or window opens | Upon clicking on the button a small windows/overlay will open | Upon clicking the button overlay doesn't get opened, but the function runs | Fail |  | 2026-01-26 | 16 | PT-3 | Test if Forum button redirects to the Forum page | 1. Press the Forum button in the navigation bar | Forum page appears. |  |  | PT-1, PT-2
18 | FO-1 | Test if the legal button works | 1. Press the legal button 2. Check if user gets directed to legal page | Upon clicking on the button the user gets directed to legal page | Upon clicking on the button the user gets directed to the legal page | Pass |  | 2026-01-26 | 17 | PR-1 | Test if profile icon opens a dropdown | 1. Click on the profile icon in the header | A dropdown menu appears with profile options. |  |  | AU-1, AU-2
19 | NL-2 | Test if subscribe to newsletter works | 1. Write an email in the newsletter input 2. Press send 3. Check if data gets stored for sending 4. Check if the button sends the data | Upon clicking the send button data get stored, data gets sent to an endpoint | Data get stored, but doesn't get sent | Fail |  | 2026-01-26 | 18 | SL-1 | Test if slider "Next" button works | 1. Navigate to the home page 2. Press the right arrow (next) button on the slider | The slider advances to the next slide. |  |  | SL-2, SL-3
20 | SO-2 | Test if facebook social icon buttons work | 1. Press the facebook icon 2. Check if the user gets directed on the facebook link connected to it | Upon clicking the button the user is directed to the facebook link | Upon clicking the button the user is directed to the facebook link | Pass |  | 2026-01-27 | 19 | SL-2 | Test if slider "Previous" button works | 1. Navigate to the home page 2. Press the left arrow (previous) button on the slider | The slider goes back to the previous slide. |  |  | SL-1, SL-3
21 | SO-3 | Test if instagram social icon buttons work | 1. Press the instagram icon 2. Check if the user gets directed on the instagram link connected to it | Upon clicking the button the user is directed to the instagram link | Upon clicking the button the user is directed to the instagram link | Pass |  | 2026-01-27 | 20 | SL-3 | Test if slider stepper (dot) buttons work | 1. Navigate to the home page 2. Click on the small dot buttons below the slider | The slider jumps to the selected slide. |  |  | SL-1, SL-2
22 | SO-4 | Test if x social icon buttons work | 1. Press the x icon 2. Check if the user gets directed on the x link connected to it | Upon clicking the button the user is directed to the x link | Upon clicking the button the user is directed to the x link | Pass |  | 2026-01-27 | 21 | BT-1 | Test if secondary button executes its click handler | 1. Navigate to the bracket page 2. Press any green secondary button 3. Check the developer console for the event | Secondary button executes its onClick function. |  |  | BT-2
23 | NL-3 | Test if subscribe to newsletter gives error message upon wrong email | 1. Write an email in the newsletter input 2. Press send 3. Check for error messages | Upon giving wrong email the newsletter gives error message |  | Hold |  | 2026-01-27 | 22 | BT-2 | Test if support button opens an overlay/window | 1. Press the support button 2. Check if an overlay or small window opens | A small overlay/window opens. |  |  | BT-1
24 | SO-1 | Test if social icons only appear if link attached to them | 1. Open the webpage 2. Scroll at the bottom 3. Check if the social icons work | Upon clicking the social icons they direct to the social page which their logo symbolises |  | Hold |  | 2026-01-27 | 23 | FO-1 | Test if Legal button redirects to the Legal page | 1. Scroll to the footer 2. Press the Legal button | User is redirected to the legal page. |  |  | SO-1, SO-2, SO-3, SO-4
25 | FT-1 | Test if featured elements can be clicked | 1. Navigate to the featured section of the home page 2. Click on an element 3. Open the devloper console and check if it says it was clicked | Upon clicking on an element it will say you clicked the following element | Upon clicking on an element it will say you clicked the following element | Pass |  | 2026-02-01 | 24 | SO-1 | Test if social icons only appear when a link is attached | 1. Open the webpage 2. Scroll to the footer 3. Check if only icons with attached links are visible | Only social icons with linked URLs are displayed. |  |  | SO-2, SO-3, SO-4
26 | FT-2 | Test if the featured section is responsive and adjusts itself. | 1. Navigate o the featured section of the home page 2. Resize the browser window 3. Check if the featured section adjusts itself | Upon resizing the window, the featured section adjusts its size and elements | Upon resizing the window, the featured section adjusts its size and elements | Pass |  | 2026-02-03 | 25 | SO-2 | Test if Facebook icon redirects correctly | 1. Scroll to the footer 2. Press the Facebook icon | User is redirected to the connected Facebook link. |  |  | SO-1, SO-3, SO-4
27 | LA-1 | Test if the English version of the site loads in | 1. Search for the site/open the site 2. Check if the site is english | Upon opening the site everything is written in english | Upon opening the site nothing appears | Fail |  | 2026-02-03 | 26 | SO-3 | Test if Instagram icon redirects correctly | 1. Scroll to the footer 2. Press the Instagram icon | User is redirected to the connected Instagram link. |  |  | SO-1, SO-2, SO-4
28 | LA-1 | Test if the English version of the site loads in | 1. Search for the site/open the site 2. Check if the site is english | Upon opening the site everything is written in english | Upon opening the site everything is written in english | Pass |  | 2026-02-03 | 27 | SO-4 | Test if X (Twitter) icon redirects correctly | 1. Scroll to the footer 2. Press the X icon | User is redirected to the connected X link. |  |  | SO-1, SO-2, SO-3
29 | LA-2 | Test if the Hungarian version of the site loads in | 1. Search for the site/open the site 2. Check if the site is hungarian | Upon opening the site everything is written in hungarian | Upon opening the site everything is written in english | Fail |  | 2026-02-03 | 28 | NL-1 | Test if newsletter subscribe button sends confirmation email | 1. Click the newsletter field 2. Enter a valid email 3. Press the subscribe button 4. Check your email | A confirmation email is sent after subscribing. |  |  | NL-2, NL-3
30 | LA-2 | Test if the Hungarian version of the site loads in | 1. Search for the site/open the site 2. Check if the site is hungarian | Upon opening the site everything is written in hungarian | Upon opening the site everything is written in hungarian | Pass |  | 2026-02-03 | 29 | NL-2 | Test if newsletter subscription sends data to the endpoint | 1. Enter a valid email in the newsletter input 2. Press send 3. Check if data is stored and sent to the backend endpoint | Data is stored and sent to the backend endpoint. |  |  | NL-1, NL-3
31 | LA-3 | Test if the German version of the site loads in | 1. Search for the site/open the site 2. Check if the site is german | Upon opening the site everything is written in german | Upon opening the site everything is written in german | Pass |  | 2026-02-03 | 30 | NL-3 | Test if newsletter shows error on invalid email input | 1. Enter an invalid email in the newsletter input 2. Press send 3. Check for an error message | An error message appears about invalid email format. |  |  | NL-1, NL-2
32 | TH-1 | Test if light and dark mode works | 1. Open the webpage 2. Find the light/dark mode toggle button on navigation bar 3. Click it 4. Check if both modes work | Upon clicking the button the theme changes | Upon clicking the button the theme won't change | Fail |  | 2026-02-03 | 31 | FT-1 | Test if featured product cards are clickable | 1. Navigate to the Featured section on the home page 2. Click on a featured product card 3. Check the developer console for a click event | The click event fires and is logged in the console. |  |  | FT-2
33 | TH-1 | Test if light and dark mode works | 1. Open the webpage 2. Find the light/dark mode toggle button on navigation bar 3. Click it 4. Check if both modes work | Upon clicking the button the theme changes | Upon clicking the button the theme changes | Pass |  | 2026-02-03 | 32 | FT-2 | Test if featured section is responsive on window resize | 1. Navigate to the Featured section on the home page 2. Resize the browser window 3. Check if the section adjusts its layout | Featured section adjusts its size and layout responsively. |  |  | FT-1, RS-5
34 | TH-2 | Test if light mode works | 1. Open the webpage 2. Find the light/dark mode toggle button on navigation bar 3. Click it 4. Check if light mode works | Upon clicking the button the theme changes | Upon clicking the button the theme changes | Pass |  | 2026-02-03 | 33 | LA-1 | Test if English version of the site loads correctly | 1. Open the site or switch language to English 2. Check that all visible text is in English | All visible text is displayed in English. |  |  | LA-2, LA-3, LA-4, LA-5
35 | TH-3 | Test if dark mode works | 1. Open the webpage 2. Find the light/dark mode toggle button on navigation bar 3. Click it 4. Check if light mode works | Upon clicking the button the theme changes | Upon clicking the button the theme changes | Pass |  | 2026-02-03 | 34 | LA-2 | Test if Hungarian version of the site loads correctly | 1. Switch language to Hungarian 2. Check that all visible text is in Hungarian | All visible text is displayed in Hungarian. |  |  | LA-1, LA-3, LA-4, LA-5
36 | LG-4 | Test if login fails when fields are empty | 1. Navigate to the login page 2. Leave email and password fields empty 3. Press the login button | Login attempt fails and an error message appears indicating required fields |  | Hold |  | 2026-02-10 | 35 | LA-3 | Test if German version of the site loads correctly | 1. Switch language to German 2. Check that all visible text is in German | All visible text is displayed in German. |  |  | LA-1, LA-2, LA-4, LA-5
37 | RG-2 | Test if registration fails when email format is invalid | 1. Navigate to the registration page 2. Enter an invalid email format 3. Fill other fields correctly 4. Press the register button | Registration fails and an error message appears about invalid email format |  | Hold |  | 2026-02-10 | 36 | LA-4 | Test if selected language persists after page reload | 1. Change the site language 2. Reload the page | Previously selected language remains active after reload. |  |  | LA-1, LA-2, LA-3, LA-5
38 | AU-1 | Test if logout works correctly | 1. Login with a valid account 2. Click on the logout button 3. Try to access a protected page | User is logged out and redirected to the login page |  | Hold |  | 2026-02-10 | 37 | LA-5 | Test if selected language persists across page navigation | 1. Change the site language 2. Navigate to different pages | Selected language remains active on all pages. |  |  | LA-1, LA-2, LA-3, LA-4
39 | WS-1 | Test if products are loaded from backend | 1. Navigate to the products page 2. Wait for products to load | Product list appears with correct product data |  | Hold |  | 2026-02-10 | 38 | TH-1 | Test if light/dark mode toggle works | 1. Open the webpage 2. Find the light/dark mode toggle on the navigation bar 3. Click it 4. Verify the theme changes | The theme changes upon clicking the toggle. |  |  | TH-2, TH-3, TH-4, TH-5
40 | WS-3 | Test if product details page opens | 1. Navigate to the products page 2. Click on a product card | Product details page opens showing product information |  | Hold |  | 2026-02-10 | 39 | TH-2 | Test if light mode applies correctly | 1. Open the webpage 2. Switch to light mode using the toggle 3. Check that the light theme is applied | Light theme is applied to the entire page. |  |  | TH-1, TH-3, TH-4, TH-5
41 | CT-1 | Test if user can add product to cart | 1. Navigate to a product details page 2. Click on “Add to cart” | Product is added to the cart and cart content updates |  | Hold |  | 2026-02-10 | 40 | TH-3 | Test if dark mode applies correctly | 1. Open the webpage 2. Switch to dark mode using the toggle 3. Check that the dark theme is applied | Dark theme is applied to the entire page. |  |  | TH-1, TH-2, TH-4, TH-5
42 | CT-2 | Test if cart updates product quantity | 1. Add a product to the cart 2. Increase or decrease product quantity | Cart updates and total price changes accordingly |  | Hold |  | 2026-02-10 | 41 | TH-4 | Test if selected theme persists after page reload | 1. Switch to dark or light mode 2. Reload the page | Previously selected theme remains active after reload. |  |  | TH-1, TH-2, TH-3, TH-5
43 | CT-5 | Test if cart can be emptied | 1. Add products to the cart 2. Click on clear cart button | Cart becomes empty and no products are displayed |  | Hold |  | 2026-02-10 | 42 | TH-5 | Test if theme state persists across page navigation | 1. Switch between light or dark mode 2. Navigate to different pages | Selected theme remains active on all pages. |  |  | TH-1, TH-2, TH-3, TH-4
44 | LA-4 | Test if selected language persists after page reload | 1. Change the site language 2. Reload the page | Previously selected language remains active |  | Hold |  | 2026-02-10 | 43 | WS-1 | Test if products are loaded from the backend | 1. Navigate to the Products page 2. Wait for products to load | Product list appears with correct product data. |  |  | WS-2, WS-3, WS-4, WS-5
45 | TH-4 | Test if dark or light mode persists after page reload | 1. Switch to dark or light mode 2. Reload the page | Previously selected theme remains active |  | Hold |  | 2026-02-10 | 44 | WS-2 | Test if empty backend response is handled on products page | 1. Navigate to the Products page 2. Simulate or receive an empty product list from the backend | A message appears indicating that no products are available. |  |  | WS-1, BE-1
46 | RS-1 | Test if navigation bar works on mobile view | 1. Resize browser window to mobile width 2. Open navigation menu 3. Click on navigation links | Navigation menu opens and links work correctly |  | Hold |  | 2026-02-10 | 45 | WS-3 | Test if product details page opens on card click | 1. Navigate to the Products page 2. Click on a product card | Product details page/modal opens showing product information. |  |  | WS-1, WS-4, WS-5
47 | RS-4 | Test if product cards are usable on mobile view | 1. Resize browser window to mobile width 2. Navigate to products page 3. Try to interact with product cards | Product cards are displayed correctly and clickable |  | Hold |  | 2026-02-10 | 46 | WS-4 | Test if product price is displayed correctly | 1. Navigate to the Products page 2. Observe the displayed prices | Product prices are displayed with correct value and currency symbol. |  |  | WS-1, WS-5
48 | BE-1 | Test if application handles backend error | 1. Disconnect backend or simulate error 2. Navigate to products page | Error message appears and application does not crash |  | Hold |  | 2026-02-10 | 47 | WS-5 | Test if out-of-stock product is handled correctly | 1. Navigate to the Products page 2. Find a product with zero stock | Product is marked as unavailable and cannot be added to cart. |  |  | WS-1, CT-1
49 | BE-2 | Test if loading indicator appears while data is loading | 1. Navigate to a page that loads data from backend 2. Observe loading state | Loading indicator appears until data is loaded |  | Hold |  | 2026-02-10 | 48 | CT-1 | Test if user can add a product to the cart | 1. Navigate to a product details page 2. Click "Add to cart" | Product is added to the cart and cart content updates. |  |  | CT-2, CT-3, CT-4, CT-5, CT-6
50 | LG-5 | Test if login fails with incorrect email format | 1. Navigate to the login page 2. Enter an invalid email format 3. Enter any password 4. Press the login button | Login attempt fails and an error message appears about invalid email format |  | Hold |  | 2026-02-10 | 49 | CT-2 | Test if cart updates product quantity correctly | 1. Add a product to the cart 2. Increase and decrease the product quantity | Cart updates and total price changes accordingly. Quantity cannot go below 1. |  |  | CT-1, CT-3, CT-4, CT-5, CT-6
51 | RG-3 | Test if registration fails when required fields are empty | 1. Navigate to the registration page 2. Leave one or more required fields empty 3. Press the register button | Registration fails and error messages appear for required fields |  | Hold |  | 2026-02-10 | 50 | CT-3 | Test if cart total price updates correctly with multiple products | 1. Add multiple products to the cart 2. Change quantities | Total price updates correctly based on cart content. |  |  | CT-1, CT-2, CT-4, CT-5, CT-6
52 | AU-2 | Test if user stays logged in after page reload | 1. Login with a valid account 2. Reload the page | User remains logged in and is not redirected to login page |  | Hold |  | 2026-02-10 | 51 | CT-4 | Test if user can remove a single product from cart | 1. Add multiple products to the cart 2. Remove one specific product | Only the selected product is removed. Other products remain in the cart. |  |  | CT-1, CT-2, CT-3, CT-5, CT-6
53 | AU-3 | Test if unauthorized user is redirected from protected page | 1. Open a protected page without logging in | User is redirected to the login page |  | Hold |  | 2026-02-10 | 52 | CT-5 | Test if cart can be fully emptied | 1. Add products to the cart 2. Click the clear/empty cart button | Cart becomes empty and no products are displayed. |  |  | CT-1, CT-2, CT-3, CT-4, CT-6
54 | WS-2 | Test if product list handles empty backend response | 1. Navigate to the products page 2. Simulate or receive an empty product list from backend | A message appears indicating that no products are available |  | Hold |  | 2026-02-10 | 53 | CT-6 | Test if cart content persists after page reload | 1. Add one or more products to the cart 2. Reload the page | Cart still contains the previously added products. |  |  | CT-1, CT-2, CT-5
55 | WS-4 | Test if product price is displayed correctly | 1. Navigate to the products page 2. Observe the displayed prices | Product prices are displayed with correct value and currency |  | Hold |  | 2026-02-10 | 54 | RS-1 | Test if navigation bar works on mobile view | 1. Resize browser window to mobile width (≤375px) 2. Open the navigation menu 3. Click on navigation links | Navigation menu opens and all links work correctly. |  |  | RS-2, RS-3, RS-4, RS-5, RS-6
56 | WS-5 | Test if out-of-stock product is handled correctly | 1. Navigate to the products page 2. Find a product with zero stock | Product is marked as unavailable and cannot be added to cart |  | Hold |  | 2026-02-10 | 55 | RS-2 | Test if navigation menu collapses on small screen | 1. Resize browser window to mobile width 2. Observe the navigation bar | Navigation menu collapses into a mobile-friendly (hamburger) menu. |  |  | RS-1, RS-3
57 | CT-6 | Test if cart content persists after page reload | 1. Add one or more products to the cart 2. Reload the page | Cart still contains the previously added products |  | Hold |  | 2026-02-10 | 56 | RS-3 | Test if navigation links work inside the mobile menu | 1. Open the mobile navigation menu 2. Click on different navigation links | User is redirected to the correct pages. |  |  | RS-1, RS-2
58 | CT-3 | Test if cart total price updates correctly | 1. Add multiple products to the cart 2. Change quantities | Total price updates correctly based on cart content |  | Hold |  | 2026-02-10 | 57 | RS-4 | Test if product cards are usable on mobile view | 1. Resize browser window to mobile width 2. Navigate to the Products page 3. Try to interact with product cards | Product cards are displayed correctly and are clickable. |  |  | RS-1, RS-5, WS-3
59 | CT-4 | Test if user can remove a single product from cart | 1. Add multiple products to the cart 2. Remove one product | Only the selected product is removed from the cart |  | Hold |  | 2026-02-10 | 58 | RS-5 | Test if product grid adjusts layout on screen resize | 1. Navigate to the Products page 2. Resize the browser window | Product grid rearranges elements without layout breaking. |  |  | RS-4, FT-2
60 | RS-2 | Test if navigation menu collapses on small screen | 1. Resize browser window to mobile width 2. Observe navigation bar | Navigation menu collapses into a mobile-friendly menu |  | Hold |  | 2026-02-10 | 59 | RS-6 | Test if text and buttons remain readable on mobile view | 1. Resize browser window to mobile size 2. Inspect text and buttons throughout the page | Text and buttons are readable and usable without overlap. |  |  | RS-1, RS-2, RS-4
61 | RS-3 | Test if navigation links work in mobile menu | 1. Open the mobile navigation menu 2. Click on different navigation links | User is redirected to the selected pages correctly |  | Hold |  | 2026-02-10 | 60 | BE-1 | Test if application handles backend errors gracefully | 1. Disconnect the backend or simulate a server error 2. Navigate to the Products page | An error message appears and the application does not crash. |  |  | BE-2, WS-1
62 | RS-5 | Test if product grid adjusts layout on screen resize | 1. Navigate to products page 2. Resize browser window | Product grid rearranges elements without layout breaking |  | Hold |  | 2026-02-10 | 61 | BE-2 | Test if loading indicator appears while data is loading | 1. Navigate to a page that loads data from the backend 2. Observe the loading state | A loading indicator appears until data is fully loaded. |  |  | BE-1, WS-1
63 | RS-6 | Test if text and buttons remain readable on mobile view | 1. Resize browser window to mobile size 2. Inspect text and buttons | Text and buttons are readable and usable without overlap |  | Hold |  | 2026-02-10 | 62 | CAT-1 | Test if product categories load correctly | 1. Navigate to the Products page 2. Observe the category list/filter panel | All available categories are displayed correctly. |  |  | CAT-2, CAT-3, CAT-4, WS-1
64 | LA-5 | Test if selected language persists across navigation | 1. Change site language 2. Navigate to different pages | Selected language remains active on all pages |  | Hold |  | 2026-02-10 | 63 | CAT-2 | Test if filtering by category works | 1. Navigate to the Products page 2. Click on a category 3. Observe the product list | Only products belonging to the selected category are displayed. |  |  | CAT-1, CAT-3, CAT-4
65 | TH-5 | Test if theme state persists across navigation | 1. Switch between light or dark mode 2. Navigate to different pages | Selected theme remains active on all pages |  | Hold |  | 2026-02-10 | 64 | CAT-3 | Test if active category is visually highlighted | 1. Navigate to the Products page 2. Click on a category | The selected category is visually distinguished (e.g. highlighted, bold, underlined). |  |  | CAT-1, CAT-2
66 | LG-4 | Test if login fails when fields are empty | 1. Navigate to the login page 2. Leave email and password fields empty 3. Press the login button | Login attempt fails and an error message appears indicating required fields | There is no error message | Fail |  | 2026-02-15 | 65 | CAT-4 | Test if selecting "All" category shows all products | 1. Navigate to the Products page 2. Select a specific category 3. Click "All" or deselect the category | All products are displayed again without any category filter. |  |  | CAT-1, CAT-2
67 | LG-4 | Test if login fails when fields are empty | 1. Navigate to the login page 2. Leave email and password fields empty 3. Press the login button | Login attempt fails and an error message appears indicating that there are fields empty | There is error message but it's empty | Fail |  | 2026-02-15 | 66 | SF-1 | Test if product search/filter by name works | 1. Navigate to the Products page 2. Enter a product name in the search field 3. Observe the product list | Only products matching the search term are displayed. |  |  | SF-2, SF-3, CAT-2
68 | LG-4 | Test if login fails when fields are empty | 1. Navigate to the login page 2. Leave email and password fields empty 3. Press the login button | Login attempt fails and an error message appears indicating that there are fields empty | Error message comes up, and shows the correct message | Pass |  | 2026-02-15 | 67 | SF-2 | Test if product sort works | 1. Navigate to the Products page 2. Select a sort option (e.g. price ascending/descending) 3. Observe the product list order | Products are reordered according to the selected sort option. |  |  | SF-1, SF-3
69 | RG-2 | Test if registration fails when email format is invalid | 1. Navigate to the registration page 2. Enter an invalid email format 3. Fill other fields correctly 4. Press the register button | Registration fails and an error message appears about invalid email format | Registration fails, and an error message | Pass |  | 2026-02-15 | 68 | SF-3 | Test if empty search result is handled correctly | 1. Navigate to the Products page 2. Enter a search term that matches no products | A message appears indicating no products were found. |  |  | SF-1, WS-2
70 | AU-1 | Test if logout works correctly | 1. Login with a valid account 2. Click on the logout button 3. Try to access a protected page | User is logged out and redirected to the login page | After logout user is redirected to login page | Pass |  | 2026-02-15 | 69 | CU-1 | Test if currency switches when language changes to English | 1. Switch language to English 2. Navigate to the Products page 3. Observe the displayed prices | Prices are displayed in USD. |  |  | CU-2, CU-3, LA-1
71 | WS-1 | Test if products are loaded from backend | 1. Navigate to the products page 2. Wait for products to load | Product list appears with correct product data | Product list appears with correct product data | Pass |  | 2026-02-15 | 70 | CU-2 | Test if currency switches when language changes to Hungarian | 1. Switch language to Hungarian 2. Navigate to the Products page 3. Observe the displayed prices | Prices are displayed in HUF. |  |  | CU-1, CU-3, LA-2
72 | WS-3 | Test if product details page opens | 1. Navigate to the products page 2. Click on a product card | Product details page opens showing product information | Product detail window opens showing the product information | Pass |  | 2026-02-15 | 71 | CU-3 | Test if currency switches when language changes to German | 1. Switch language to German 2. Navigate to the Products page 3. Observe the displayed prices | Prices are displayed in EUR. |  |  | CU-1, CU-2, LA-3
73 | CT-1 | Test if user can add product to cart | 1. Navigate to a product details page 2. Click on “Add to cart” | Product is added to the cart and cart content updates | User can add product but it the cart won't show it | Fail |  | 2026-02-15 | 72 | CU-4 | Test if currency conversion displays correct value | 1. Note the base HUF price of a product 2. Switch to English (USD) or German (EUR) 3. Compare the converted price | Converted price matches the expected exchange rate value. |  |  | CU-1, CU-2, CU-3
74 | CT-1 | Test if user can add product to cart | 1. Navigate to a product details page 2. Click on “Add to cart” | Product is added to the cart and cart content updates | User can add product but wrong product data gets shown | Fail |  | 2026-02-15 | 73 | TS-1 | Test if success toast appears on successful action | 1. Perform a successful action (e.g. add to cart, login) 2. Observe the screen | A success toast notification appears and disappears after a short time. |  |  | TS-2, TS-3
75 | CT-1 | Test if user can add product to cart | 1. Navigate to a product details page 2. Click on “Add to cart” | Product is added to the cart and cart content updates | Product is added to the cart and cart content updates | Pass |  | 2026-02-15 | 74 | TS-2 | Test if error toast appears on failed action | 1. Perform a failing action (e.g. login with wrong credentials) 2. Observe the screen | An error toast notification appears and disappears after a short time. |  |  | TS-1, TS-3
76 | CT-2 | Test if cart updates product quantity | 1. Add a product to the cart 2. Increase or decrease product quantity | Cart updates and total price changes accordingly | Cart updates, but can be negative value | Fail |  | 2026-02-15 | 75 | TS-3 | Test if toast disappears automatically | 1. Trigger any toast notification 2. Wait without interacting | The toast notification disappears automatically after its timeout. |  |  | TS-1, TS-2
77 | CT-2 | Test if cart updates product quantity | 1. Add a product to the cart 2. Increase or decrease product quantity | Cart updates and total price changes accordingly | Cart updates but can't increase | Fail |  | 2026-02-15 | 76 | FR-1 | Test if forum posts load correctly | 1. Navigate to the Forum page 2. Wait for posts to load | Forum posts are displayed with title, body and author. |  |  | FR-2, FR-3, FR-4
78 | CT-2 | Test if cart updates product quantity | 1. Add a product to the cart 2. Increase or decrease product quantity | Cart updates and total price changes accordingly | Cart updates and total price changes accordingly | Pass |  | 2026-02-15 | 77 | FR-2 | Test if logged-in user can create a new forum post | 1. Log in 2. Navigate to the Forum page 3. Fill in the post form 4. Submit the post | New post appears in the forum list. |  |  | FR-1, FR-3, AU-1
79 | CT-5 | Test if cart can be emptied | 1. Add products to the cart 2. Click on clear cart button | Cart becomes empty and no products are displayed | Cart becomes empty and no products are displayed | Pass |  | 2026-02-15 | 78 | FR-3 | Test if forum post creation is blocked for guests | 1. Open the Forum page without logging in 2. Try to create a post | Post creation is blocked or the form is not available for unauthenticated users. |  |  | FR-2, AU-3
80 | LA-4 | Test if selected language persists after page reload | 1. Change the site language 2. Reload the page | Previously selected language remains active | Previously selected language remains active | Pass |  | 2026-02-15 | 79 | FR-4 | Test if empty forum post list is handled correctly | 1. Navigate to the Forum page 2. Simulate or receive an empty post list | A message appears indicating there are no posts yet. |  |  | FR-1
81 | TH-4 | Test if dark or light mode persists after page reload | 1. Switch to dark or light mode 2. Reload the page | Previously selected theme remains active | Themes become inversed | Fail |  | 2026-02-15 | 80 | PE-1 | Test if user can edit their name from profile | 1. Log in 2. Navigate to the profile page 3. Change first or last name 4. Save changes | Name is updated and the new name is displayed. |  |  | PE-2, PR-1
82 | TH-4 | Test if dark or light mode persists after page reload | 1. Switch to dark or light mode 2. Reload the page | Previously selected theme remains active | Previously selected theme remains active | Pass |  | 2026-02-15 | 81 | PE-2 | Test if profile page displays correct user data | 1. Log in 2. Navigate to the profile page | Profile page shows the correct email, name and account details. |  |  | PE-1, PR-1
83 | LG-5 | Test if login fails with incorrect email format | 1. Navigate to the login page 2. Enter an invalid email format 3. Enter any password 4. Press the login button | Login attempt fails and an error message appears about invalid email format | Login attempt fails and an error message appears about invalid email format | Pass |  | 2026-02-15 | 82 | DA-1 | Test if user can initiate account deletion | 1. Log in 2. Navigate to the profile/settings page 3. Click on delete account 4. Confirm deletion | Account deletion email or confirmation step is triggered. |  |  | DA-2, AU-1
84 | RG-3 | Test if registration fails when required fields are empty | 1. Navigate to the registration page 2. Leave one or more required fields empty 3. Press the register button | Registration fails and error messages appear for required fields | Registration fails and error messages appear for required fields | Pass |  | 2026-02-15 | 83 | DA-2 | Test if deleted account cannot log in | 1. Delete an account 2. Try to log in with the deleted account credentials | Login fails with an appropriate error message. |  |  | DA-1, LG-1
85 | AU-2 | Test if user stays logged in after page reload | 1. Login with a valid account 2. Reload the page | User remains logged in and is not redirected to login page | User remains logged in and is not redirected to login page | Pass |  | 2026-02-15 | 84 | IM-1 | Test if product images load correctly | 1. Navigate to the Products page 2. Observe the product card images | Product images are displayed correctly for all products. |  |  | IM-2, WS-1
86 | WS-2 | Test if product list handles empty backend response | 1. Navigate to the products page 2. Simulate or receive an empty product list from backend | A message appears indicating that no products are available | A message appears indicating that no products are available | Pass |  | 2026-02-15 | 85 | IM-2 | Test if placeholder image shows when product image is missing | 1. Navigate to the Products page 2. Find or simulate a product with no image | A placeholder/fallback image is displayed instead of a broken image. |  |  | IM-1, WS-1
87 | WS-4 | Test if product price is displayed correctly | 1. Navigate to the products page 2. Observe the displayed prices | Product prices are displayed with correct value and currency | Wrong value getting displayed | Fail |  | 2026-02-15 | 86 | OR-1 | Test if user can proceed to checkout from cart | 1. Add products to the cart 2. Navigate to the cart 3. Click the checkout/order button | Checkout page or order form appears. |  |  | OR-2, OR-3, CT-1
88 | WS-4 | Test if product price is displayed correctly | 1. Navigate to the products page 2. Observe the displayed prices | Product prices are displayed with correct value and currency | Wrong value format getting displayed | Fail |  | 2026-02-15 | 87 | OR-2 | Test if order form requires all mandatory fields | 1. Navigate to the checkout page 2. Leave required fields empty 3. Try to submit | Submission is blocked and error messages appear for empty required fields. |  |  | OR-1, OR-3
89 | WS-4 | Test if product price is displayed correctly | 1. Navigate to the products page 2. Observe the displayed prices | Product prices are displayed with correct value and currency | Wrong value format getting displayed | Fail |  | 2026-02-15 | 88 | OR-3 | Test if order is placed successfully with valid data | 1. Navigate to the checkout page 2. Fill in all required fields correctly 3. Submit the order | Order is placed and a confirmation message or page appears. |  |  | OR-1, OR-2
90 | WS-4 | Test if product price is displayed correctly | 1. Navigate to the products page 2. Observe the displayed prices | Product prices are displayed with correct value and currency | Product prices are displayed with correct value and currency | Pass |  | 2026-02-15 | 89 | NF-1 | Test if 404 page appears on unknown route | 1. Navigate to a URL that does not exist (e.g. /doesnotexist) | 404 Not Found page is displayed. |  |  | PT-1, PT-2, PT-3
91 | WS-5 | Test if out-of-stock product is handled correctly | 1. Navigate to the products page 2. Find a product with zero stock | Product is marked as unavailable and cannot be added to cart | Product is marked as unavailable and cannot be added to cart | Pass |  | 2026-02-15 | 90 | AD-1 | Test if admin page is accessible for admin users | 1. Log in with an admin account 2. Navigate to the admin page | Admin page loads correctly. |  |  | AD-2, AD-3
92 | CT-6 | Test if cart content persists after page reload | 1. Add one or more products to the cart 2. Reload the page | Cart still contains the previously added products | Cart still contains the previously added products | Pass |  | 2026-02-15 | 91 | AD-2 | Test if admin page is blocked for regular users | 1. Log in with a regular (non-admin) account 2. Try to navigate to the admin page | Access is denied and user is redirected away from the admin page. |  |  | AD-1, AU-3
93 | CT-3 | Test if cart total price updates correctly | 1. Add multiple products to the cart 2. Change quantities | Total price updates correctly based on cart content | Total price updates correctly based on cart content | Pass |  | 2026-02-15 | 92 | AD-3 | Test if admin can manage products (add/edit/delete) | 1. Log in as admin 2. Navigate to the admin panel 3. Try to add, edit or delete a product | Product management actions execute successfully and changes are reflected. |  |  | AD-1, WS-1
94 | CT-4 | Test if user can remove a single product from cart | 1. Add multiple products to the cart 2. Remove one product | Only the selected product is removed from the cart | Only the selected product is removed from the cart | Pass |  | 2026-02-15
95 | RS-6 | Test if text and buttons remain readable on mobile view | 1. Resize browser window to mobile size 2. Inspect text and buttons | Text and buttons are readable and usable without overlap | Text and buttons are readable and usable without overlap | Pass |  | 2026-02-15
96 | LA-5 | Test if selected language persists across navigation | 1. Change site language 2. Navigate to different pages | Selected language remains active on all pages | Selected language remains active on all pages but somewhere remains on other languages | Fail |  | 2026-02-15
97 | TH-5 | Test if theme state persists across navigation | 1. Switch between light or dark mode 2. Navigate to different pages | Selected theme remains active on all pages | Selected theme remains active on all pages | Pass |  | 2026-02-15
98 | LA-5 | Test if selected language persists across navigation | 1. Change site language 2. Navigate to different pages | Selected language remains active on all pages | Selected language remains active on all pages | Pass |  | 2026-02-15
99 | RS-1 | Test if navigation bar works on mobile view | 1. Resize browser window to mobile width 2. Open navigation menu 3. Click on navigation links | Navigation menu opens and links work correctly |  | Hold |  | 2026-02-15
100 | RS-4 | Test if product cards are usable on mobile view | 1. Resize browser window to mobile width 2. Navigate to products page 3. Try to interact with product cards | Product cards are displayed correctly and clickable |  | Hold |  | 2026-02-15
101 | AU-3 | Test if unauthorized user is redirected from protected page | 1. Open a protected page without logging in | User is redirected to the login page |  | Hold |  | 2026-02-15
102 | RS-2 | Test if navigation menu collapses on small screen | 1. Resize browser window to mobile width 2. Observe navigation bar | Navigation menu collapses into a mobile-friendly menu |  | Hold |  | 2026-02-15
103 | RS-3 | Test if navigation links work in mobile menu | 1. Open the mobile navigation menu 2. Click on different navigation links | User is redirected to the selected pages correctly |  | Hold |  | 2026-02-15
104 | RS-5 | Test if product grid adjusts layout on screen resize | 1. Navigate to products page 2. Resize browser window | Product grid rearranges elements without layout breaking |  | Hold |  | 2026-02-15
105 | RS-6 | Test if text and buttons remain readable on mobile view | 1. Resize browser window to mobile size 2. Inspect text and buttons | Text and buttons are readable and usable without overlap |  | Hold |  | 2026-02-15
99 | RS-1 | Test if navigation bar works on mobile view | 1. Resize browser window to mobile width 2. Open navigation menu 3. Click on navigation links | Navigation menu opens and links work correctly | Navigation menu opens and links work correctly | Pass |  | 2026-02-17
100 | RS-4 | Test if product cards are usable on mobile view | 1. Resize browser window to mobile width 2. Navigate to products page 3. Try to interact with product cards | Product cards are displayed correctly and clickable | Product cards are displayed correctly and clickable | Pass |  | 2026-02-17
101 | AU-3 | Test if unauthorized user is redirected from protected page | 1. Open a protected page without logging in | User is redirected to the login page | User is redirected to the login page | Pass |  | 2026-02-17
102 | RS-2 | Test if navigation menu collapses on small screen | 1. Resize browser window to mobile width 2. Observe navigation bar | Navigation menu collapses into a mobile-friendly menu | Navigation menu collapses into a mobile-friendly menu | Pass |  | 2026-02-17
103 | RS-3 | Test if navigation links work in mobile menu | 1. Open the mobile navigation menu 2. Click on different navigation links | User is redirected to the selected pages correctly | User is redirected to the selected pages correctly | Pass |  | 2026-02-17
104 | RS-5 | Test if product grid adjusts layout on screen resize | 1. Navigate to products page 2. Resize browser window | Product grid rearranges elements without layout breaking | Product grid rearranges elements without layout breaking | Pass |  | 2026-02-17
105 | RS-6 | Test if text and buttons remain readable on mobile view | 1. Resize browser window to mobile size 2. Inspect text and buttons | Text and buttons are readable and usable without overlap | Text and buttons are readable and usable without overlap | Pass |  | 2026-02-17
106 | LG-1 | Test if login works with valid credentials | 1. Navigate to the login page 2. Enter a valid existing email 3. Enter the correct password 4. Press the login button | Login attempt succeeds. A success notification appears. | Login promise not working, url is in a bad format | Fail | LG-2, LG-3, LG-4, LG-5 | 2026-02-21
107 | LG-1 | Test if login works with valid credentials | 1. Navigate to the login page 2. Enter a valid existing email 3. Enter the correct password 4. Press the login button | Login attempt succeeds. A success notification appears. | Login promise not working, url is in a bad format | Fail | LG-2, LG-3, LG-4, LG-5 | 2026-02-21
108 | LG-1 | Test if login works with valid credentials | 1. Navigate to the login page 2. Enter a valid existing email 3. Enter the correct password 4. Press the login button | Login attempt succeeds. A success notification appears. | Login promise not working, url is in a bad format | Fail | LG-2, LG-3, LG-4, LG-5 | 2026-02-21
109 | LG-1 | Test if login works with valid credentials | 1. Navigate to the login page 2. Enter a valid existing email 3. Enter the correct password 4. Press the login button | Login attempt succeeds. A success notification appears. | Login promise not working, url is in a bad format | Fail | LG-2, LG-3, LG-4, LG-5 | 2026-02-21
110 | LG-1 | Test if login works with valid credentials | 1. Navigate to the login page 2. Enter a valid existing email 3. Enter the correct password 4. Press the login button | Login attempt succeeds. A success notification appears. | Login promise not working, url is in a bad format | Fail | LG-2, LG-3, LG-4, LG-5 | 2026-02-21
111 | LG-1 | Test if login works with valid credentials | 1. Navigate to the login page 2. Enter a valid existing email 3. Enter the correct password 4. Press the login button | Login attempt succeeds. A success notification appears. | Login promise not working, url is in a bad format | Fail | LG-2, LG-3, LG-4, LG-5 | 2026-02-21
112 | LG-1 | Test if login works with valid credentials | 1. Navigate to the login page 2. Enter a valid existing email 3. Enter the correct password 4. Press the login button | Login attempt succeeds. A success notification appears. | Login promise not working, url is wrong | Fail | LG-2, LG-3, LG-4, LG-5 | 2026-02-21
113 | LG-1 | Test if login works with valid credentials | 1. Navigate to the login page 2. Enter a valid existing email 3. Enter the correct password 4. Press the login button | Login attempt succeeds. A success notification appears. | Login promise not working, url is wrong | Fail | LG-2, LG-3, LG-4, LG-5 | 2026-02-21
114 | LG-1 | Test if login works with valid credentials | 1. Navigate to the login page 2. Enter a valid existing email 3. Enter the correct password 4. Press the login button | Login attempt succeeds. A success notification appears. | Login promise not working, url is wrong | Fail | LG-2, LG-3, LG-4, LG-5 | 2026-02-21
115 | LG-1 | Test if login works with valid credentials | 1. Navigate to the login page 2. Enter a valid existing email 3. Enter the correct password 4. Press the login button | Login attempt succeeds. A success notification appears. | Login promise not working, url is wrong | Fail | LG-2, LG-3, LG-4, LG-5 | 2026-02-21
116 | LG-1 | Test if login works with valid credentials | 1. Navigate to the login page 2. Enter a valid existing email 3. Enter the correct password 4. Press the login button | Login attempt succeeds. A success notification appears. | Login promise not working, url is wrong | Fail | LG-2, LG-3, LG-4, LG-5 | 2026-02-21
117 | LG-1 | Test if login works with valid credentials | 1. Navigate to the login page 2. Enter a valid existing email 3. Enter the correct password 4. Press the login button | Login attempt succeeds. A success notification appears. | Login promise not working, url is wrong | Fail | LG-2, LG-3, LG-4, LG-5 | 2026-02-21
118 | LG-1 | Test if login works with valid credentials | 1. Navigate to the login page 2. Enter a valid existing email 3. Enter the correct password 4. Press the login button | Login attempt succeeds. A success notification appears. | Login promise not working, url is wrong | Fail | LG-2, LG-3, LG-4, LG-5 | 2026-02-21
119 | LG-1 | Test if login works with valid credentials | 1. Navigate to the login page 2. Enter a valid existing email 3. Enter the correct password 4. Press the login button | Login attempt succeeds. A success notification appears. | Login promise not working, url is wrong | Fail | LG-2, LG-3, LG-4, LG-5 | 2026-02-21
120 | LG-1 | Test if login works with valid credentials | 1. Navigate to the login page 2. Enter a valid existing email 3. Enter the correct password 4. Press the login button | Login attempt succeeds. A success notification appears. | Login promise not working, url is wrong | Fail | LG-2, LG-3, LG-4, LG-5 | 2026-02-21
121 | LG-1 | Test if login works with valid credentials | 1. Navigate to the login page 2. Enter a valid existing email 3. Enter the correct password 4. Press the login button | Login attempt succeeds. A success notification appears. | Login promise not working, url is wrong | Fail | LG-2, LG-3, LG-4, LG-5 | 2026-02-21
122 | LG-1 | Test if login works with valid credentials | 1. Navigate to the login page 2. Enter a valid existing email 3. Enter the correct password 4. Press the login button | Login attempt succeeds. A success notification appears. | Login promise not working, url is wrong | Fail | LG-2, LG-3, LG-4, LG-5 | 2026-02-21
123 | LG-1 | Test if login works with valid credentials | 1. Navigate to the login page 2. Enter a valid existing email 3. Enter the correct password 4. Press the login button | Login attempt succeeds. A success notification appears. | Login promise not working, url is wrong | Fail | LG-2, LG-3, LG-4, LG-5 | 2026-02-21
124 | LG-1 | Test if login works with valid credentials | 1. Navigate to the login page 2. Enter a valid existing email 3. Enter the correct password 4. Press the login button | Login attempt succeeds. A success notification appears. | Login works, user gets logged in, success notification appears | Pass | LG-2, LG-3, LG-4, LG-5 | 2026-02-21
28 | NL-1 | Test if newsletter subscribe button sends confirmation email | 1. Click the newsletter field 2. Enter a valid email 3. Press the subscribe button 4. Check your email | A confirmation email is sent after subscribing. | There is no email which gets sent | Fail | NL-2, NL-3 | 2026-02-23
28 | NL-1 | Test if newsletter subscribe button sends confirmation email | 1. Click the newsletter field 2. Enter a valid email 3. Press the subscribe button 4. Check your email | A confirmation email is sent after subscribing. | There is no email which gets sent | Fail | NL-2, NL-3 | 2026-02-23
28 | NL-1 | Test if newsletter subscribe button sends confirmation email | 1. Click the newsletter field 2. Enter a valid email 3. Press the subscribe button 4. Check your email | A confirmation email is sent after subscribing. | There is no email which gets sent | Fail | NL-2, NL-3 | 2026-02-23
28 | NL-1 | Test if newsletter subscribe button sends confirmation email | 1. Click the newsletter field 2. Enter a valid email 3. Press the subscribe button 4. Check your email | A confirmation email is sent after subscribing. | There is no email which gets sent | Fail | NL-2, NL-3 | 2026-02-23
28 | NL-1 | Test if newsletter subscribe button sends confirmation email | 1. Click the newsletter field 2. Enter a valid email 3. Press the subscribe button 4. Check your email | A confirmation email is sent after subscribing. | There is no email which gets sent | Fail | NL-2, NL-3 | 2026-02-23
28 | NL-1 | Test if newsletter subscribe button sends confirmation email | 1. Click the newsletter field 2. Enter a valid email 3. Press the subscribe button 4. Check your email | A confirmation email is sent after subscribing. | There is no email which gets sent | Fail | NL-2, NL-3 | 2026-02-23
28 | NL-1 | Test if newsletter subscribe button sends confirmation email | 1. Click the newsletter field 2. Enter a valid email 3. Press the subscribe button 4. Check your email | A confirmation email is sent after subscribing. | There is no email which gets sent | Fail | NL-2, NL-3 | 2026-02-23
28 | NL-1 | Test if newsletter subscribe button sends confirmation email | 1. Click the newsletter field 2. Enter a valid email 3. Press the subscribe button 4. Check your email | A confirmation email is sent after subscribing. | A confirmation email is sent after subscribing. | Pass | NL-2, NL-3 | 2026-02-23

## Backend
ID | Task ID | Test Objective | Test Steps | Expected Result | Actual Result | Pass/Fail | Related tasks | Date
1 | TI-1 | Test if api/registration_request works | 1. Open postman 2. Send a request to http://localhost:90/api/registration_promise/ with the body „ { "email": "<b64encoded email> "password": "<b64 encoded password>", "firstname":"b64 encoded firstname", "lastname":"b64 encoded lastname" } | Response: 200 (OK), body: „email kuldve <email>” Registers the user, makes it unverified and sends an email | Response: 200 (OK), body: „email kuldve <email>” Registers the user, makes it unverified and sends an email | Pass | TI-2,TI-10,TI-11 | 2025-11-17
2 | TI-2 | Test if api/registration_promise works | 1. Open postman 2. Send a request to http://localhost:90/api/registration_promise/ with the body „ { "email": "<b64encoded email "token": "<b64 encoded token parsed from url>" } | Response: 200 (OK), body: „aktivalva” Changes the account’s status from unverified to verified | Response: 200 (OK), body: „aktivalva” Changes the account’s status from unverified to verified | Pass |  | 2025-11-18
3 | TI-3 | Test if api/chpass_request works | 1. Open postman 2. Send a request to http://localhost:90/api/chpass_request/ with the body „ { "email": "<b64encoded email”, "password": "<b64 encoded password>" } | Response: 200 (OK), body: „email_kuldve" Creates a new confirmation, and sends an email | Response: 200 (OK), body: „email_kuldve" Creates a new confirmation, and sends an email | Pass | TI-12 | 2025-11-18
4 | TI-4 | Test if api/chpass_promise works | 1. Open postman 2. Send a request to http://localhost:90/api/chpass_promise/ with the body „ { "id": "<b64encoded user_id”, "token": "<b64 encoded confirmation_token>" } | Response: 200 (OK), body: „jelszo_megvaltoztatva" Changes the user's password, deletes confirmation | Response: 200 (OK), body: „jelszo_megvaltoztatva" Changes the user's password, deletes confirmation | Pass | TI-15,TI-16 | 2025-11-18
5 | TI-5 | Test if api/login works | 1. Open postman 2. Send a request to http://localhost:90/api/chpass_promise/ with the body „ { "id": "<b64encoded email”, "password": "<b64 encoded password_hash>" } | Response: 200 (OK), body: „email kuldve" Sends email | Response: 200 (OK), body: „email kuldve" Sends email | Pass | TI-13 | 2025-11-19
6 | TI-6 | Test if api/delacc_request works | 1. Open postman 2. Send a request to http://localhost:90/api/delacc_request/ with the body „ { "id": "<b64encoded id”, "password": "<b64 encoded password_hash>" } | Response: 200 (OK), body: „email kuldve" Sends email | Response: 200 (OK), body: „email kuldve" Sends email | Pass | TI-14,T-38 | 2025-11-19
7 | TI-7 | Test if api/delacc_promise works | 1. Open postman 2. Send a request to http://localhost:90/api/delacc_promise/ with the body „ { "id": "<b64encoded id”, "password": "<b64 encoded token>" } | Response: 200 (OK), body: „felhasznalo_torolve" Deletes account | Response: 200 (OK), body: „felhasznalo_torolve" Deletes account | Pass | TI-6,T-39 | 2025-11-21
8 | TI-8 | Test if add_test_users works (test panel) works | 1. Open the Test panel 2. Click add test users | It adds 33 test users | It adds 33 test users | Pass |  | 2025-11-21
9 | TI-9 | Test if delete_all_users works (test panel) works | 1. Open the Test panel 2. Click delete all users | It deletes all existing users | It deletes all existing users | Pass |  | 2025-11-22
10 | TI-10 | Test if api/registration_request works (duplicate user) | 1. Open postman 2. Send a request to http://localhost:90/api/registration_promise/ with the body „ { "email": "<b64encoded email> "password": "<b64 encoded password>", "firstname":"b64 encoded firstname", "lastname":"b64 encoded lastname" } | Response: 401 (UNATHORIZED), body: „felhasznalo_mar_letezik” | Response: 401 (UNATHORIZED), body: „felhasznalo_mar_letezik” | Pass | TI-1,TI-11 | 2025-12-14
11 | TI-11 | Test if api/registration_request works (malformed request) | 1. Open postman 2. Send a request to http://localhost:90/api/registration_promise/ with the body „ { "email": "<b64encoded email> "password": "gtfofvjhgturifjvghuifk", "firstname":"b64 encoded firstname", "lastname":"b64 encoded lastname" } | Response: 400 (BAD REQUEST), body: „hibas_request” | Response: 400 (BAD REQUEST), body: „hibas_request” | Pass | TI-1,TI-10 | 2025-12-14
12 | TI-12 | Test if api/chpass_request works (with a nonexisting user) | 1. Open postman 2. Send a request to http://localhost:90/api/chpass_request/ with the body „ { "email": "<b64encoded email”, "password": "<b64 encoded password>" } | Response: 500 (ISE), body: „sze_v_felhasznalo_nem_letezik" | Response: 500 (OK), body: „sze_v_felhasznalo_nem_letezik" | Pass | TI-3 | 2025-12-15
13 | TI-13 | Test if api/login works (wrong password) | 1. Open postman 2. Send a request to http://localhost:90/api/chpass_promise/ with the body „ { "id": "<b64encoded email”, "password": "<b64 encoded password_hash>" } | Response: 401 (UNATHORIZED), body: „hibas_jelszo" Sends email | Response: 401 (UNATHORIZED), body: „hibas_jelszo" Sends email | Pass | TI-5 | 2025-12-15
14 | TI-14 | Test if api/delacc_request works (with a nonexisting user) | 1. Open postman 2. Send a request to http://localhost:90/api/delacc_request/ with the body „ { "id": "<b64encoded id”, "password": "<b64 encoded password_hash>" } | Response: 500 (OK), body: „sze_v_felhasznalo_nem_letezik" | Response: 500 (OK), body: „sze_v_felhasznalo_nem_letezik" | Pass | TI-6,T-38 | 2025-12-15
15 | TI-15 | Test if api/chpass_promise works (wrong token) | 1. Open postman 2. Send a request to http://localhost:90/api/chpass_promise/ with the body „ { "id": "<b64encoded user_id”, "token": "<b64 encoded confirmation_token>" } | Response: 400 (BAD REQUEST), body: „hibas_token" | Response: 400 (BAD REQUEST), body: „hibas_token" | Pass | TI-4,TI-16,T-39 | 12.16.2025
16 | TI-16 | Test if api/chpass_promise works (nonexistent confirmation) | 1. Open postman 2. Send a request to http://localhost:90/api/chpass_promise/ with the body „ { "id": "<b64encoded user_id”, "token": "<b64 encoded confirmation_token>" } | Response: 404 (NOT FOUND), body: „confirmation_nem_letezik_vagy_hibas" | Response: 404 (NOT FOUND), body: „confirmation_nem_letezik_vagy_hibas" | Pass | TI-4,TI-15 | 12.16.2025
17 | TI-17 | Test if api/chpass_promise works (expired confirmation) | 1. Open postman 2. Send a request to http://localhost:90/api/chpass_promise/ with the body „ { "id": "<b64encoded user_id”, "token": "<b64 encoded confirmation_token>" } | Response: 410 (GONE), body: „confirmation_lejart" | Response: 410 (GONE), body: „confirmation_lejart" | Pass | TI-4 | 12.16.2025
18 | TI-18 | Test if add_test_products works (test panel) | 1. Open the Test panel 2. Click add products | It adds 33 test products | It adds 33 test products | Pass |  | 2026-01-12
19 | TI-19 | Test if add_test_orders works (test panel) | 1. Open the Test panel 2. Click add test orders | It adds 33 test orders | It adds 33 test orders | Pass | T-31 | 2026-01-12
20 | TI-20 | Test if api/registration_promise works (wrong token) | 1. Open postman 2. Send a request to http://localhost:90/api/chpass_promise/ with the body „ { "id": "<b64encoded user_id”, "token": "<wrong b64 encoded confirmation_token>" } | Response: 401 (UNATHORIZED), body: „hibas_token" | Response: 401 (UNATHORIZED), body: „hibas_token" | Pass | TI-2,TI-10,TI-11,TI-21,TI-22 | 20.01.2026
21 | TI-21 | Test if api/registration_promise works (user already activated) | 1. Open postman 2. Send a request to http://localhost:90/api/chpass_promise/ with the body „ { "id": "<b64encoded user_id”, "token": "<b64 encoded confirmation_token>" } | Response: 409 (CONFLICT), body: „felhasznalo_mar_aktivalva" | Response: 409 (CONFLICT), body: „felhasznalo_mar_aktivalva" | Pass | TI-2,TI-10,TI-11 | 20.01.2026
22 | TI-22 | Test if api/registration_promise works (wrong/nonexistent id) | 1. Open postman 2. Send a request to http://localhost:90/api/chpass_promise/ with the body „ { "id": "<b64encoded user_id”, "token": "<random b64 encoded confirmation_token>" } | Response: 404 (NOT FOUND), body: „felhasznalo_nem_letezik" | Response: 401 (UNATHORIZED), body: „hibas_token" | Fail | TI-2,TI-10,TI-11,TI-23 | 20.01.2026
23 | TI-23 | Test if api/registration_promise works (wrong/nonexistent id) | 1. Open postman 2. Send a request to http://localhost:90/api/chpass_promise/ with the body „ { "id": "<b64encoded user_id”, "token": "<random b64 encoded confirmation_token>" } | Response: 404 (NOT FOUND), body: „felhasznalo_nem_letezik" | Response: 404 (NOT FOUND), body: „felhasznalo_nem_letezik" | Pass | TI-2,TI-10,TI-11,TI-22 | 20.01.2026
24 | TI-24 | Test if add test confirmations (test panel) works | 1. Open the Test panel 2. Click the add test confirmations button | It adds 33 test confirmations | It adds 33 test confirmations | Pass | TI-25, T-32 | 2026-02-03
25 | TI-25 | Test if delete all confirmations (test panel) works | 1. Open the Test panel 2. Click the delete all confirmations button | It deletes all existing confirmations | It deletes all existing confirmations | Pass | TI-24, T-32 | 2026-02-03
26 | TI-26 | Test if delete all products (test panel) works | 1. Open the Test panel 2. Click the delete all products button | It deletes all existing products | It deletes all existing products | Pass | TI-18 | 2026-02-03
27 | TI-27 | Test if delet all orders (test panel) works | 1. Open the Test panel 2. Click the delete all orders button | It deletes all existing products | It deletes all existing products | Pass | TI-19 | 2026-02-03
29 | TI-29 | Test if add test product images works | 1. Open the Test panel 2. Type in the product id 3. Click the add test prod. Image button | It adds 3 test product images to the right product | It adds 3 test product images to the right product | Pass | T-30 | 2026-02-12
30 | TI-30 | Test if delete all test product images works | 1. Open the Test panel 2. Click the delete all test prod. Image button | It deletes all existing product images | It deletes all existing product images | Pass | T-29 | 2026-02-12
31 | TI-31 | Test if add_test_orders works | 1. Open the Test panel 2. Type in the user id 3. Click the add test orders button | It adds 33 test orders to the correct user | It adds 33 test orders to the correct user | Pass | T-19 | 2026-02-12
32 | T-32 | Test if add test confirmations (test panel) works | 1. Open the Test panel 2. Type in the start user id (the id of the first user, the first out of 33 users with consequent user id’s) 3. Click the add test confirmations button | It adds 33 test confirmations to 33 different users | It adds 33 test confirmations to 33 different users | Pass | TI-25, T-24 | 2026-02-12
33 | T-33 | Test if add test reviews (test panel) works | 1. Open the Test panel 2. Type in the user id 3. Click the add test confirmations button | It adds 33 test reviews to the correct product | It adds 33 test reviews to the correct product | Pass | TI-25, T-24 | 2026-02-12
33 | T-33 | Test if api/get_all_products works | 1. Open postman 2. Send a request to http://localhost:90/api/get_all_products/ without a body and auth header | Response: 200 (OK), body: „{ "statuscode": "200", "status": "no error", "products": [ «correctly formatted products here» ] }" (json response) | Response: 200 (OK), body: „{ "statuscode": "200", "status": "no error", "products": [ «correctly formatted products here» ] }" (json response) | Pass | TI-25, T-24 | 2026-02-12
35 | T-35 | Test if api/registration_promise works | 1. Open postman 2. Send a request to http://localhost:90/api/registration_promise/ with the body „ { "email": "<b64encoded email "token": "<b64 encoded token parsed from url>" } | Response: 200 (OK), body: „aktivalva” Changes the account’s status from unverified to verified | Response: 200 (OK), body: „aktivalva” Changes the account’s status from unverified to verified | Pass |  | 2026-02-12
36 | T-36 | Test if api/chpass_request works | 1. Open postman 2. Send a request to http://localhost:90/api/chpass_request/ with the body „ { "email": "<b64encoded email”, "password": "<b64 encoded password>" } | Response: 200 (OK), body: „email_kuldve" Creates a new confirmation, and sends an email | Response: 200 (OK), body: „email_kuldve" Creates a new confirmation, and sends an email | Pass | TI-12 | 2026-02-12
36 | T-36 | Test if api/chpass_promise works | 1. Open postman 2. Send a request to http://localhost:90/api/chpass_promise/ with the body „ { "id": "<b64encoded user_id”, "token": "<b64 encoded confirmation_token>" } | Response: 200 (OK), body: „jelszo_megvaltoztatva" Changes the user's password, deletes confirmation | Response: 200 (OK), body: „jelszo_megvaltoztatva" Changes the user's password, deletes confirmation | Pass | TI-15,TI-16 | 2025-11-18
37 | T-37 | Test if api/login works | 1. Open postman 2. Send a request to http://localhost:90/api/chpass_promise/ with the body „ { "id": "<b64encoded email”, "password": "<b64 encoded password>" } without an auth header | Response: 200 (OK), body: „{ "token": "«token here»", "expires_in": 604800 }" Sends email | Response: 200 (OK), body: „{ "token": "«token here»", "expires_in": 604800 }" Sends email | Pass | TI-13 | 2026-02-12
38 | T-38 | Test if api/delacc_request works | 1. Open postman 2. Send a request to http://localhost:90/api/delacc_request/ with the body „ { "id": "<b64encoded id”, "password": "<b64 encoded password>" } with an auth header | Response: 200 (OK), body: „email kuldve" Sends email | Response: 200 (OK), body: „email kuldve" Sends email | Pass | TI-14 | 2026-02-12
39 | T-39 | Test if api/delacc_promise works | 1. Open postman 2. Send a request to http://localhost:90/api/delacc_promise/ with the body „ { "id": "<b64encoded id”, "password": "<b64 encoded token>" } with an auth header | Response: 200 (OK), body: „felhasznalo_torolve" Deletes account | Response: 200 (OK), body: „felhasznalo_torolve" Deletes account | Pass | TI-6 | 2026-02-12
57 | T-57 | Test if api/delacc_request works (wrong or expired auth token in header) | 1. Open postman 2. Send a request to http://localhost:90/api/delacc_request/ with the body „ { "id": "<b64encoded id”, "password": "<b64 encoded password>" } with an auth header | Response: 401 (UNATHORIZED), body: „hibas_token" Does not send the email | Response: 200 (OK), body: „email kuldve" Sends email | Fail | TI-14 | 2026-02-12
58 | T-58 | Test if api/delacc_promise works (wrong or expired auth token in header) | 1. Open postman 2. Send a request to http://localhost:90/api/delacc_promise/ with the body „ { "id": "<b64encoded id”, "password": "<b64 encoded token>" } with an auth header | Response: 401 (UNATHORIZED), body: „hibas_token" Did not delete account | Response: 200 (OK), body: „felhasznalo_torolve" Deletes account | Fail | TI-6 | 2026-02-12
59 | T-59 | Test if api/delacc_request works (wrong or expired auth token in header) | 1. Open postman 2. Send a request to http://localhost:90/api/delacc_request/ with the body „ { "id": "<b64encoded id”, "password": "<b64 encoded password>" } with an auth header | Response: 401 (UNATHORIZED), body: „hibas_token" Does not send the email | Response: 401 (UNATHORIZED), body: „hibas_token" Does not send the email | Pass | TI-14 | 2026-02-12
39 | T-39 | Test if api/delacc_promise works (wrong or expired auth token in header) | 1. Open postman 2. Send a request to http://localhost:90/api/delacc_promise/ with the body „ { "id": "<b64encoded id”, "password": "<b64 encoded token>" } with an auth header | Response: 401 (UNATHORIZED), body: „hibas_token" Did not delete account | Response: 401 (UNATHORIZED), body: „hibas_token" Did not delete account | Pass | TI-6 | 2026-02-12
40 | T-40 | Test if Test email (test panel) works | 1. Open the Test panel 2. Type in the email 3. Click the Test email button | It sends a test email | It sends a test email | Pass |  | 2026-02-12
41 | T-41 | Test if Test magic link (test panel) works | 1. Open the Test panel 2. Type in the email 3. Click the Test magic link button | It sends a test email with a specific code and displays that code in a textbox next to the email field | It doesn’t do anything | Fail |  | 2026-02-12
42 | T-42 | Test if Test magic link (test panel) works | 1. Open the Test panel 2. Type in the email 3. Click the Test magic link button | It sends a test email with a specific code and displays that code in a textbox next to the email field | It sends a test email with a specific code and displays that code in a textbox next to the email field | Pass |  | 2026-02-13
43 | T-43 | Test if api/get_all_product_categories works | 1. Open postman 2. Send a request to http://localhost:90/api/get_all_product_categories/ without a body or an auth header | It returns all the product categories | It returns all the product categories | Pass | T-44 | 2026-02-20
44 | T-44 | Test if api/get_all_product_categories works (malformed request body) | 1. Open postman 2. Send a request to http://localhost:90/api/get_all_product_categories/ with the body „ { "id": "<b64encoded id”, "passwo | It returns all the product categories | It returns all the product categories | Pass | T-43 | 2026-02-20
45 | T-45 | Test if api/get_all_featured_products works | 1. Open postman 2. Send a request to http://localhost:90/api/get_all_product_categories/ without a body or an s_featured | It returns all the featured products and their important data | It returns all the featured products and their important data | Pass | T-46 | 2026-02-20
46 | T-46 | Test if api/get_all_featured_products works (malformed request) | 1. Open postman 2. Send a request to http://localhost:90/api/get_all_product_categories/ with the body „ { "id": "<b64encoded i” | It returns all the featured products and their important data just fine | It returns all the featured products and their important data just fine | Pass | T-45 | 2026-02-20
47 | T-47 | Test if api/get_all_users works | 1. Open postman 2. Send a request to https://localhost:90/api/get_all_users with the body „{ "id":"<b64 encoded id of an admin user>", "session_token":"<b64 encoded token of the same admin user>" }” and an auth header: „Bearer <correct jwt token of the same admin user>” | It returns all the users and their data | It returns all the users and their data | Pass | T-48, T-49, T-50 | 2026-02-20
48 | T-48 | Test if api/get_all_users works (non admin user) | 1. Open postman 2. Send a request to https://localhost:90/api/get_all_users with the body „{ "id":"<b64 encoded id of a non-admin user>", "session_token":"<b64 encoded token of the same user>" }” and an auth header: „Bearer <correct jwt token of the same user>” | Response: {"status":"permission_denied","statuscode":401} | Response: {"status":"permission_denied","statuscode":401} | Pass | T-47, T-49, T-50 | 2026-02-20
49 | T-49 | Test if api/get_all_users works (missing auth header) | 1. Open postman 2. Send a request to https://localhost:90/api/get_all_users with the body „{ "id":"<b64 encoded id of a non-admin user>", "session_token":"<b64 encoded token of the same user>" }” and no auth header | Response: „hianyzo_auth_header", statuscode: 401 (UNATHORIZED) | Response: „hianyzo_auth_header", statuscode: 401 (UNATHORIZED) | Pass | T-50, T-47, T-48 | 2026-02-20
50 | T-50 | Test if api/get_all_users works (malformed request) | 1. Open postman 2. Send a request to https://localhost:90/api/get_all_users with the body „{ "id":"<b64 encoded id of a non-admin user>” and an auth header | Response: {"status":"malformed_request","statuscode":"400"} | Response: {"status":"malformed_request","statuscode":"400"} | Pass | T-47, T-48, T-49 | 2026-02-20
51 | T-51 | Test if api/get_all_orders works (missing body, auth header) | 1. Open postman 2. Send a request to https://localhost:90/api/get_all_orders without a body and an auth header | Response: 401 (UNATHORIZED), body: „hianyzo_auth_header” | Response: 401 (UNATHORIZED), body: „hianyzo_auth_header” | Pass | T-52,T-53 | 2026-02-21
52 | T-52 | Test if api/get_all_orders works (correct request data) | 1. Open postman 2. Send a request to https://localhost:90/api/get_all_orders with the body „{ "id":"<id of an admin user>", "session_token":"<token of an admin user>" }” and an auth header | Response: 200 (OK), body: „{ "statuscode": "200", "status": "success", "orders": [<all of the orders>] }" | Response: 200 (OK), body: „{ "statuscode": "200", "status": "success", "orders": [<all of the orders>] }" | Pass | T-53,T-51 | 2026-02-21
53 | T-53 | Test if api/get_all_orders works (non-admin user) | 1. Open postman 2. Send a request to https://localhost:90/api/get_all_orders with the body „{ "id":"<id of a non-admin user>", "session_token":"<token of a non-admin user>" }” and an auth header | Response: 401 (UNATHORIZED), body: „{"status":"permission_denied","statuscode":401}" | Response: 401 (UNATHORIZED), body: „{"status":"permission_denied","statuscode":401}" | Pass | T-51,T-52 | 2026-02-21
54 | T-54 | Test if api/newsletter_subscription works (malformed request) | 1. Open postman 2. Send a request to http://localhost:90/api/newsletter_subscription/ with the body „ { "id": "<b64encoded i” | Response: 400 (BAD REQUEST), body: „{"status":"malformed_request","statuscode":"400"}" | Response: 400 (BAD REQUEST), body: „{"status":"malformed_request","statuscode":"400"}" | Pass | T-55,T-56 | 2026-02-26
55 | T-55 | Test if api/newsletter_subscription works (duplicate user) | 1. Open postman 2. Send a request to http://localhost:90/api/newsletter_subscription/ with the body „ { "email": "<base64 encoded email>", "news_level": "<base64 encoded string:2>", "language": "<base64 encoded string:en>" }” | Response: 409 (CONFLICT), body: „{"status":"user_already_subscribed","statuscode":"409"}" | Response: 400 (BAD REQUEST), body: „{"status":"user_already_subscribed","statuscode":"409"}" | Pass | T-54,T-56 | 2026-02-26
56 | T-56 | Test if api/newsletter_subscription works | 1. Open postman 2. Send a request to http://localhost:90/api/newsletter_subscription/ with the body „ { "email": "<base64 encoded email>", "news_level": "<base64 encoded string:2>", "language": "<base64 encoded string:en>" }” | Response: 200 (SUCCESS), body: „{ "status": "success", "statuscode": "200" }" | Response: 200 (SUCCESS), body: „{ "status": "success", "statuscode": "200" }" | Pass | T-54,T-55 | 2026-02-26
60

## Database
ID | Task ID | Test Objective | Test Steps | Expected Result | Actual Result | Pass/Fail | Related tasks | Date
1 | SP-1 | Test if create_account works | 1. Go to PHPMyAdmin 2. Call create_account with the required data (first_name, last_name, email, sesstoken, passhash, sesstoken_expire, account_state) | It creates a new row in the users table, with the inputted data | It creates a new row in the users table, with the inputted data | Pass | SP-4, SP-5 | 2025-11-11
2 | SP-2 | Test if create_confirmation works | 1. Go to PHPMyAdmin 2. Call create_confirmation with the required data (confirmation_token, identification, new_value, type) | It creates a new row in the confirmations table, with the inputted data | It creates a new row in the confirmations table, with the inputted data | Pass |  | 2025-11-11
3 | SP-3 | Test if create_post works | 1. Go to PHPMyAdmin 2. Call create_post with the required data (body, title, user_id, image_source) | It creates a new row in the posts table, with the inputted data | It creates a new row in the posts table, with the inputted data | Pass | SP-6 | 2025-11-11
4 | SP-4 | Test if delete_account_by_email works | 1. Go to PHPMyAdmin 2. Call delete_account_by_email with the target user’s email | It deletes the targeted row from users table | It deletes the targeted row from users table | Pass | SP-5, SP-1 | 2025-11-11
5 | SP-5 | Test if delete_account_by_id works | 1. Go to PHPMyAdmin 2. Call delete_account_by_id with the target user’s id | It deletes the targeted row from users table | It deletes the targeted row from users table | Pass | SP-4, SP-1 | 2025-11-11
6 | SP-6 | Test if delete_post_by_id works | 1. Go to PHPMyAdmin 2. Call delete_delete_post_by_id with the target post’s id | It deletes the targeted row from posts table | It deletes the targeted row from posts table | Pass | SP-3 | 2025-11-11
7 | SP-7 | Test if get_all_confirmations works | 1. Go to PHPMyAdmin 2. Call get_all_confirmations | It returns all of the rows from the confirmations table | It returns all of the rows from the confirmations table | Pass | SP-2 | 2025-11-11
8 | SP-8 | Test if create_product works | 1. Go to PHPMyAdmin 2. Call create_product with the required data (name, description, price, times_ordered, image_source, stock, sale_price, description_preview) | It creates a new row in the products table, with the inputted data | It creates a new row in the products table, with the inputted data | Pass | SP-9 | 2025-11-11
9 | SP-9 | Test if create_order_item works | 1. Go to PHPMyAdmin 2. Call create_order_item with the required data (order_id, product_id, quantity) | It creates a new row in the order_items table, with the inputted data and calculates the price based on quantity and the price in the products table referenced with the product_id | It creates a new row in the order_items table, with the inputted data and calculates the price based on quantity and the price in the products table referenced with the product_id | Pass | SP-8, SP-10 | 2025-11-11
10 | SP-10 | Test if get_all_order_items works | 1. Go to PHPMyAdmin 2. Call get_all_order_items | It returns all of the rows from the order_items table | It returns all of the rows from the order_items table | Pass | SP-9 | 2025-11-11
11 | SP-11 | Test if create_order works | 1. Go to PHPMyAdmin 2. Call create_order(user_id, city, zipcode, address, apartment_number, note, house number) | It creates a new row in the orders table, with the inputted data, with price 0 and created at is the current time | It creates a new row in the orders table, with the inputted data, with price 0 and created at is the current time | Pass | SP-9 | 2025-11-13
12 | SP-12 | Test if get_all_orders works | 1. Go to PHPMyAdmin 2. Call get_all_orders | It returns all of the rows from the orders table | It returns all of the rows from the orders table | Pass | SP-11 | 2025-11-13
13 | SP-13 | Test if update_order_price works | 1. Go to PHPMyAdmin 2. Call update_order_price(id) | It calculates the price for the given order, based on all order_items’ price that share the same order id | It calculates the price for the given order, based on all order_items’ price that share the same order id | Pass | SP-8, SP-9, SP-11 | 2025-11-13
14 | SP-14 | Test if get_all_posts works | 1. Go to PHPMyAdmin 2. Call get_all_posts | It returns all of the rows from the posts table | It returns all of the rows from the posts table | Pass | SP-3 | 2025-11-13
15 | SP-15 | Test if get_all_products works | 1. Go to PHPMyAdmin 2. Call get_all_products | It returns all of the rows from the products table | It returns all of the rows from the posts table | Pass | SP-8, SP-3 | 2025-11-18
16 | SP-16 | Test if get_all_users works | 2. Go to PHPMyAdmin 2. Call get_all_products | It returns all of the rows from the users table | It returns all of the users from the posts table | Pass | SP-1 | 2025-11-18
17 | SP-17 | Test if get_confirmation_by_id works | 1. Go to PHPMyAdmin 2. Call get_confirmation_by_id with the desired confirmation’s id | It returns the row with the given id from the confirmations table | It returns all of the users from the confirmations table | Pass | SP-2 | 2025-11-18
18 | SP-18 | Test if get_order_by_id works | 1. Go to PHPMyAdmin 2. Call get_order_by_id with the desired order’s id | It returns the row with the given id from the orders table | It returns all of the users from the orders table | Pass | SP-11 | 2025-11-18
19 | SP-19 | Test if get_order_item_by_id works | 1. Go to PHPMyAdmin 2. Call get_order_item_by_id(id) | It returns the row with the given id from the order_items table | It returns all of the users from the orders table | Pass | SP-9 | 2025-11-18
20 | SP-20 | Test if get_order_items_by_order_id works | 1. Go to PHPMyAdmin 2. Call get_order_items_by_order_id(order_id) | It returns all of the rows row with the given order_id from the order_items table | It returns all of the rows row with the given order_id from the order_items table | Pass | SP-9 | 2025-11-18
21 | SP-21 | Test if get_post_by_id works | 1. Go to PHPMyAdmin 2. Call get_post_by_id(id) | It returns the row with the given id from the posts table | It returns the row with the given id from the posts table | Pass | SP-3 | 2025-11-18
22 | SP-22 | Test if get_product_by_id works | 1. Go to PHPMyAdmin 2. Call get_product_by_id(id) | It returns the row with the given id from the products table | It returns the row with the given id from the products table | Pass | SP-8 | 2025-11-18
23 | SP-23 | Test if get_user_by_id works | 1. Go to PHPMyAdmin 2. Call get_user_by_id(id) | It returns the row with the given id from the users table | It returns the row with the given id from the users table | Pass | SP-1 | 2025-11-18
24 | SP-24 | Test if refresh_token works | 1. Go to PHPMyAdmin 2. Call refresh_token(id, new_sesstoken) | It updates the sesstoken_expiration by 1 week and updates the sesstoken for the new value for the row with the given id in the users table | It updates the sesstoken_expiration by 1 week and updates the sesstoken for the new value for the row with the given id | Pass | SP-1 | 2025-11-18
25 | SP-25 | Test if update_name_by_id works | 1. Go to PHPMyAdmin 2. Call update_name_by_id(id, firstname, lastname) | It updates the first and last name of the row with the given id in the users table | It updates the first and last name of the row with the given id in the users table | Pass | SP-1 | 2025-11-18
26 | SP-26 | Test if update_account_state_by_id works | 1. Go to PHPMyAdmin 2. Call update_account_state_by_id(id, new account_state) | It updates the account_state of the row with the given id in the users table | It updates the account_state of the row with the given id in the users table | Pass | SP-1 | 2025-11-18
27 | SP-27 | Test if update_password_by_id works | 1. Go to PHPMyAdmin 2. Call update_password_by_id(id, new_passhash) | It updates the passhash of the row with the given id in the users table | It updates the passhash of the row with the given id in the users table | Pass | SP-1 | 2025-11-18
28 | SP-28 | Test if update_product_stock_by_id works | 1. Go to PHPMyAdmin 2. Call update_product_stock_by_id(id, new_stock) | It updates the stock of the row with the given id in the products table | It updates the stock of the row with the given id in the products table | Pass | SP-8, SP-9, SP-13 | 2025-11-18
29 | SP-29 | Test if update_user_by_id works | 1. Go to PHPMyAdmin 2. Call update_account with the required data (account_state, email first_name, last_name, sesstoken, passhash, id) | It updates the row with the given id in the users table with the inputted data | It updates the row with the given id in the users table with the inputted data | Pass | SP-1 | 2025-11-18
30 | SP-30 | Test if delete_all_users works | 1. Go to PHPMyAdmin 2. Call delete_all_users | Deletes all the rows from the users table | Deletes all the rows from the users table | Pass | SP-1, SP-4, SP-5 | 2025-11-18
31 | SP-31 | Test if delete_all_orders works | 1. Go to PHPMyAdmin 2. Call delete_all_orders | Deletes all the rows from the orders table | Deletes all the rows from the orders table | Pass |  | 2025-11-18
32 | SP-32 | Test if delete_all_order_items works | 1. Go to PHPMyAdmin 2. Call delete_all_order_items | Deletes all the rows from the order_items table | Deletes all the rows from the order_items table | Pass |  | 2025-11-18
33 | SP-33 | Test if delete_all_posts works | 1. Go to PHPMyAdmin 2. Call delete_all_posts | Deletes all the rows from the posts table | Deletes all the rows from the posts table | Pass |  | 2025-11-18
34 | SP-34 | Test if delete_all_confirmations works | 1. Go to PHPMyAdmin 2. Call delete_all_confirmations | Deletes all the rows from the confirmations table | Deletes all the rows from the confirmations table | Pass |  | 2025-11-18
35 | SP-35 | Test if delete_all_posts works | 1. Go to PHPMyAdmin 2. Call delete_all_posts | Deletes all the rows from the posts table | Deletes all the rows from the posts table | Pass |  | 2025-11-18
36 | SP-36 | Test if get_user_by_email works | 1. Go to PHPMyAdmin 2. Call get_user_by_email with the required data (email) | Returns the desired user from the users table | Returns the desired user from the users table | Pass | SP-23, SP-1 | 2026-01-06
37 | SP-37 | Test if get_confirmations_by_identification works | 1. Go to PHPMyAdmin 2. Call get_confirmations_by_identification with the required data (identification) | Returns every row with the inputted identification from the confirmations table |  | Pending |  | 2026-01-06
38 | SP-38 | Test if update_order_item_quantity works | 1. Go to PHPMyAdmin 2. Call update_order_item_quantity with the required data (id, new_quantity) | Updates the item quantity in order_items table where row matches id | Updates the item quantity in order_items table where row matches id | Pass | SP-9 | 2026-01-06
39 | SP-39 | Test if get_confirmations_by_identification_and_type works | 1. Go to PHPMyAdmin 2. Call get_confirmation_by_identification_and_type with the required data (id, identification_type) | Returns every row with the inputted identification and type from the confirmations table | Returns every confirmation with the inputted identification and type | Pass |  | 2026-01-06
40 | SP-40 | Test if get_confirmations_by_identification works | 1. Go to PHPMyAdmin 2. Call get_confirmations_by_identification with the required data (identification) | Returns every row with the inputted identification from the confirmations table | Returns every row with the inputted identification from the confirmations table | Pass | SP-37 | 2026-01-06
41 | SP-41 | Test if update_post_by_id works | 1. Go to PHPMyAdmin 2. Call update_post_by_id(id, new_title, new_body, new_user_id, new_created_at, new_image_source) | Updates the row from posts table where row id matches inputted id | Updates the row from posts table where row id matches inputted id | Pass |  | 2026-01-06
42 | SP-42 | Test if delete_all_products works | 1. Go to PHPMyAdmin 2. Call delete_all_products | Deletes all the rows from the products table | Deletes all the rows from the products table | Pass |  | 2026-01-09
43 | SP-43 | Test if ban_user_by_id works | 1. Go to PHPMyAdmin 2. Call ban_user_by_id(id) | Sets account state to banned for the row that has the same id | Sets account state to banned for the row that has the same id | Pass | SP-1, SP-26 | 2026-01-09
44 | SP-44 | Test if delete_expired_confirmations works | 1. Go to PHPMyAdmin 2. Call delete_expired_confirmations | Deletes every row from the confirmations table where the token Is expired | Deletes every row from the confirmations table where the token Is expired | Pass |  | 2026-01-09
45 | SP-45 | Test if get_posts_by_user | 1. Go to PHPMyAdmin 2. Call delete_expired_confirmations(user_id) | Returns every post with the given user_id from the posts table | Returns every post with the given user_id from the posts table | Pass |  | 2026-01-09
46 | SP-46 | Test if create_order_item works | 1. Go to PHPMyAdmin 2. Call create_order_item with the required data (order_id, product_id, quantity) | The procedure takes into account if the product is on sale and calculates the price based on that | The procedure only uses the non sale price | Failed |  | 2026-01-12
47 | SP-47 | Test if create_order_item works | 1. Go to PHPMyAdmin 2. Call create_order_item with the required data (order_id, product_id, quantity) | The procedure takes into account if the product is on sale and calculates the price based on that | The procedure takes into account if the product is on sale and calculates the price based on that | Pass | SP-46 | 2026-01-12
48 | SP-48 | Test if get_all_verified_users works | 1. Go to PHPMyAdmin 2. Call get_all_verified_users | Returns every row from the users table where the account_state is ‘verified’ | Returns every row from the users table where the account_state is ‘verified’ | Pass |  | 2026-01-20
49 | SP-49 | Test if calculate_order_price works | 1. Go to PHPMyAdmin 2. Call calculate_order_price with the required data (id) | Calculates the final price of the order based the order_items prices associated with the order with order_id | Calculates the final price of the order based the order_items prices associated with the order with order_id | Pass |  | 2026-01-20
50 | SP-50 | Test if delete_confirmation_by_id works | 1. Go to PHPMyAdmin 2. Call delete_confirmation_by_id with the required data (id) | It deletes the targeted row from the confirmations table | It deletes the targeted row from the confirmations table | Pass |  | 2026-01-20
51 | SP-51 | Test if delete_confirmation_by_user_id works | 1. Go to PHPMyAdmin 2. Call delete_confirmation_by_user_id with the required data (user _id) | It deletes the rows from the confirmations table with the given user_id | It deletes the row from the confirmations table with the given user_id | Pass |  | 2026-01-20
52 | SP-52 | Test if delete_confirmation_by_user_id_and_type works | 1. Go to PHPMyAdmin 2. Call delete_confirmation_by_user_id_and_type with the required data (user _id, confirmation_type) | It deletes the rows from the confirmations table with the given user_id and confirmation_type | It deletes the rows from the confirmations table with the given user_id and confirmation_type | Pass |  | 2026-01-20
53 | SP-53 | Test if delete_order_by_id works | 1. Go to PHPMyAdmin 2. Call delete_order_by_id with the required data (id) | It deletes the row from the orders table with the given id | It deletes the row from the orders table with the given id | Pass |  | 2026-01-20
54 | SP-54 | Test if delete_order_item_by_id works | 1. Go to PHPMyAdmin 2. Call delete_order_item_by_id with the required data (id) | It deletes the row from the order_items table with the given id | It deletes the row from the order_items table with the given id | Pass |  | 2026-01-20
55 | SP-55 | Test if disable_account_by_id works | 1. Go to PHPMyAdmin 2. Call disable_account_by_id with the required data (id) | It sets the account to deleted and nulls email, passhash, sesstoken and sesstoken_expire | Cannot null the email, passhash, sesstoken and sesstoken_expire | Failed |  | 2026-01-20
56 | SP-56 | Test if disable_account_by_id works | 2. Go to PHPMyAdmin 2. Call disable_account_by_id with the required data (id) | It sets the account to deleted and sets passhash, sesstoken and sesstoken_expire to ‘deleted field’ | It sets the account to deleted and sets passhash, sesstoken and sesstoken_expire to ‘deleted field’ | Pass |  | 2026-01-20